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Exhibit 99.1

Bitdeer Announces August 2025 Production and Operations Update

- Increased self-mining hashrate by 35% to 30.0 EH/s on continued deployment of SEALMINERs

SINGAPORE, September 12, 2025 (GLOBE NEWSWIRE) -- Bitdeer Technologies Group (NASDAQ: BTDR) (“Bitdeer” or the “Company”), a world-leading technology company for Bitcoin mining, today announced its unaudited mining and operations updates for August 2025.

Operational Update

· Self-mined Bitcoin: 375 Bitcoins, an increase of ~33% from July 2025 due to higher average self-mining hashrate from energization of SEALMINERs.

· Mining Rig Manufacturing and R&D:

· SEALMINER A1: 4.1 EH/s have been energized.

· SEALMINER A2:

· Total of 27.8 EH/s in mining rigs have been manufactured and an additional 1.2 EH/s are in final assembly as of end of August 2025.

· Of the 27.8 EH/s mining rigs that have been manufactured:

· External-sales: 6.0 EH/s of mining rigs have been shipped to external customers, including 0.1 EH/s that were shipped in August.

· Self-mining:

· 18.0 EH/s of mining rigs have been deployed in U.S., Tydal, Norway and Jigmeling, Bhutan, including 7.8 EH/s in August 2025.

· 2.7 EH/s of mining rigs are in-transit to Bitdeer’s sites in Norway and Bhutan.

· 1.1 EH/s of mining rigs are being prepared for shipping.

· SEALMINER A3:

· In final stages of preparation for mass production which is expected to begin in late September or early October.

· Machine level testing results meeting expectations.

· The specific machine models and specifications will be announced alongside mass production.

· SEALMINER A4:

· On track to achieve an expected chip efficiency of approximately 5 J/TH.

· Planning two different chip designs of SEAL04 to ensure success.

· U.S. Manufacturing: Bitdeer’s U.S. factory is actively in planning and preparation.
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· HPC/AI:

· Entered into advanced negotiations with a development partner regarding our Clarington, Ohio site.

· Bitdeer.AI, the Company’s neo cloud business, reached US$8 million AI cloud ARR (annualized run-rate revenue) in August from providing GPU cloud services, with significant growth expected from Q4 2025.

· 8 NVL72 servers are being installed in Malaysia and are expected to start serving customers in Q4 2025.

· Successfully launched Relational Database Service (RDS). Actively developing AI Agent and Retrieval-Augmented Generation (RAG) technologies to enhance knowledge base and AI cloud services.

· Investigating deployment of modular data centers at Wenatchee, Washington facility.

· Hosting:

· The hosted hash rate remained unchanged in August 2025.

· Infrastructure:

· Tydal, Norway (Hydro): 161 MW is online. The remaining 14 MW is expected to be energized by the end of Q3 2025.

· Jigmeling, Bhutan: 367.5 MW is online, with the remaining 132.5 MW expected to be energized in phases by the end of Q3 2025.

Management Commentary

“Our operational team continues to execute and we are well on our way to achieving our ambitious target of 40 EH/s of self-mining by the end of October 2025.” said Matt Kong, Chief Business Officer at Bitdeer. “However, we’re not stopping there. Over the coming quarters, we will continue expanding our SEALMINER fleet into our near-term global power capacity, putting us on track to become one of the largest vertically integrated miners in the world.”

	Production and Operations Summary
	
	
	
	
	
	

	
	
	August
	July
	August

	Metrics
	
	2025
	
	2025
	
	2024
	

	Total hash rate under management1 (EH/s)
	
	44.2
	36.4
	16.8

	- Proprietary hash rate
	30.3
	22.5
	8.6

	● Self-mining
	30.0
	22.3
	7.8

	● Cloud Hash Rate
	-
	-
	0.8

	● Delivered but not hashing
	0.3
	0.2
	-

	- Hosting
	13.9
	13.9
	8.2

	Mining rigs under management
	229,000
	213,000
	167,000

	- Self-owned2
	143,000
	127,000
	87,000

	- Hosted
	86,000
	86,000
	80,000

	Bitcoins mined (self-mining only)
	375
	282
	166

	Bitcoin held3
	1,934
	1,667
	290



· Total hash rate under management as of August 31, 2025 across the Company’s primary business lines: Self-mining, Cloud Hash Rate, and Hosting.

· Self-mining refers to cryptocurrency mining for the Company’s own account, which allows it to directly capture the high appreciation potential of cryptocurrency.

· Cloud Hash Rate offers hash rate subscription plans and shares mining income with customers under certain arrangements. The Cloud Hash Rate stated above reflects the contracted hash rate with customers at month-end.

· Hosting encompasses a one-stop mining machine hosting solution including deployment, maintenance, and management services for efficient cryptocurrency mining.

· Self-owned mining machines are for the Company’s self-mining business and Cloud Hash Rate business.

· Bitcoins held do not include the Bitcoins from deposits of the customers. 2
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Infrastructure Construction Update


Site / Location
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Electrical capacity
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· Rockdale, Texas

· Knoxville, Tennessee

· Wenatchee, Washington

· Molde, Norway

· Tydal, Norway

· Gedu, Bhutan

· Jigmeling, Bhutan

Total electrical capacity Pipeline capacity

· Tydal, Norway

· Massillon, Ohio

· Clarington, Ohio

· Jigmeling, Bhutan
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-Rockdale, Texas

-Alberta, Canada
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-Oromia Region, Ethiopia

Total pipeline capacity
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Total global electrical capacity

· Indicative timing. All timing references are to calendar quarters and years.
· Figures represent total available electrical capacity.
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Capacity

(MW)
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563

86

13

84

211

100

367.5

1,424.55

14

221

570

132.5

179

99

50

1,265.5

2,690





	Status
	
	Timing4

	Online
	Completed

	Online
	Completed

	Online
	Completed

	Online
	Completed

	Online
	Completed

	Online
	Completed

	Online
	Completed

	In progress
	Q3 2025

	In progress
	Q1 2026

	In progress
	Q2 2027

	In progress
	Q3 2025

	In planning
	Estimate 2026

	In planning
	Q4 2026

	In progress
	Q4 2025



Rockdale, Texas – 100 MW Hydro-cooling conversion has been fully energized.

Tydal, Norway – 175 MW site expansion has commenced energization and the full energization timeline has been adjusted to the end of Q3 2025:

· 161 MW is online.

· All equipment has been delivered. The remaining 14 MW is expected to be energized by the end of Q3 2025.

Massillon, Ohio – 221 MW site is under construction and the full energization timeline has been adjusted to the end of Q1 2026 due to transformer delivery delays, labor storages and anticipated cold winter months:

· 21MW is expected to be energized by the end of October 2025.

· The remaining 200MW is expected to be energized in phases by the end of Q1 2026.

Clarington, Ohio – 570 MW under contract – power and datacenter infrastructure to be completed in Q2 2027.

Jigmeling, Bhutan – 500 MW site has commenced energization and is expected to be fully energized in phases by the end of Q3 2025:

· 367.5 MW is online.

· The remaining 132.5 MW is expected to be energized in phases by the end of Q3 2025.

· Two 132kV transformers and five 220kV transformers have been energized in June 2025.

· Delivery of containers and hydro-cooling systems have been completed and are now being installed.

Fox Creek, Alberta – 101 MW site acquired in Alberta, is fully licensed and permitted to construct an on-site natural gas power plant. The project is expected to be energized by the end of Q4 2026.

Oromia Region, Ethiopia – SPA and a turnkey agreement signed for the acquisition and construction of a 50 MW Bitcoin mining project in Ethiopia. The project is expected to be energized in Q4 2025.

Upcoming Conferences and Events

· October 7, 2025: CEO Summit in Phoenix

· November 10 – 12, 2025: Cantor Crypto, AI/Energy Infrastructure Conference in Miami

· January 13 – 16, 2026: 28th Annual Needham Growth Conference in New York

About Bitdeer Technologies Group

Bitdeer is a world-leading technology company for Bitcoin mining. Bitdeer is committed to providing comprehensive Bitcoin mining solutions for its customers. Bitdeer handles complex processes involved in computing such as equipment procurement, transport logistics, datacenter design and construction, equipment management, and daily operations. Bitdeer also offers advanced cloud capabilities to customers with high demand for artificial intelligence. Headquartered in Singapore, Bitdeer has deployed datacenters in the United States, Norway, and Bhutan. To learn more, visit https://ir.bitdeer.com/ or follow Bitdeer on X @ BitdeerOfficial and LinkedIn @ Bitdeer Group.

Investors and others should note that Bitdeer may announce material information using its website and/or on its accounts on social media platforms, including X, formerly known as Twitter, Facebook, and LinkedIn. Therefore, Bitdeer encourages investors and others to review the information it posts on the social media and other communication channels listed on its website.
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Forward-Looking Statements

Statements in this press release about future expectations, plans, and prospects, as well as any other statements regarding matters that are not historical facts, may constitute “forward-looking statements” within the meaning of The Private Securities Litigation Reform Act of 1995. The words “anticipate,” “look forward to,” “believe,” “continue,” “could,” “estimate,” “expect,” “intend,” “may,” “plan,” “potential,” “predict,” “project,” “should,” “target,” “will,” “would” and similar expressions are intended to identify forward-looking statements, although not all forward-looking statements contain these identifying words. Actual results may differ materially from those indicated by such forward-looking statements as a result of various important factors, including factors discussed in the section entitled “Risk Factors” in Bitdeer’s annual report on Form 20-F, as well as discussions of potential risks, uncertainties, and other important factors in Bitdeer’s subsequent filings with the U.S. Securities and Exchange Commission. Any forward-looking statements contained in this press release speak only as of the date hereof. Bitdeer specifically disclaims any obligation to update any forward-looking statement, whether due to new information, future events, or otherwise. Readers should not rely upon the information on this page as current or accurate after its publication date.

For investor and media inquiries, please contact:

Investor Relations

Orange Group

Yujia Zhai

bitdeerIR@orangegroupadvisors.com

Media

Elev8 New Media

Jessica Starman, MBA

bitdeer@elev8newmedia.com

Public Relations

BlocksBridge Consulting

Nishant Sharma

bitdeer@blocksbridge.com
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